## Plan my tasks
Week | Task work
2022-07-11
Create a spreadsheet to store my work plan
Create a new Trello board for "Building a CI/CD Pipeline" project
Create a new repo: "Building a CI/CD Pipeline" to store my code
17/11/2022
Create the Makefile for my "Building a CI/CD Pipeline" repo
Create the requirements.txt file for my repo
Create hello.py and test_hello.py file for my repo
Create the Python Virtual Environment for running makefile and take screenshot
21/11/2022
Set up GitHub Actions: create main.yml for run after push code and take run successful screenshot
Add the GitHub Actions badge to the README file in my repo
Download and push Flask code to my repo
Setting environment and run app
Push app to App Service in Azure
Update make_predict_azure_app.sh
28/11/2022
Set up the Azure DevOps pipeline and makesure it working
Update document with README file
Submit project 2 DevOps
Goals
Finish my project 2 DevOps