## Plan my tasks
Week | Tasks | Difficulty
2022-07-11
| Set up github account, permission | 1
| Set up code | 2
17/11/2022
| Train team about existing code | 1
| Estimate budget | 1
| Get approval for budget | 1
| Create azure resources | 2
21/11/2022
| Set up CI pipeline | 2
| Test CI pipeline | 1
28/11/2022
| Set up CD pipeline | 3
| Test CD pipeline | 1
| Update documents | 2
| Release and demo | 1
| Goals of quarter | Goals of year | Difficulty | Project manager guidelines
| Setup CI/CD | Deploy version successful | 1 : Easy | Demo every monday
| Demo and document | Enhance to deploy multi evironment | 2 : Middle | Report to team daily
3: Difficult